## Outline (hidden)
CRP | DMC Overview | Angio Case | Instance | What's not there | DMC | Staging Area | Data Validation | Scenarios
(Greg)
Objectives | SCP Family | Architecture | DM | All attributes | UI | Structure | History Qty Match | Forecast Source change
Schedule |  | Data Flow | -Access | UOM |  | Demarkation | Item Match | Item Change
Roles |  | What's not there |  | Notes | Dimensions | - DMC ONLY | Customer/Sites match | Booking Changes - Dates, Qty, Cancellation, Creation
Artifacts |  |  | EBS DEV | EBS Load | Levels, Attribute |  | Monthly buckets | Item transition GLF >> QBY
What's not there |  |  |  |  | Measures |  | PTO Items | Forecast generation
[5 empty] | Tables/Reports |  | Capital Items | Fcst Models used
[7 empty] | Forecast Source | Adjust History and re-run Fcst
Mid-cycle History refresh
Metrics
Archiving
Marketing Override Process
Forecast to EBS
EBS Load
Objective
  Familiarize yourself with DM Cloud application
  Validate
    Data Modeling
    Process
    Data Flow
  Check the limited development objects already in place
  Execute test scenarios
  Identify issues
Schedule
  2 weeks (Gantt including milestones within CRP)
  How many sessions?
  Agenda
Artifacts
  CRP Issue Log
  DM Cloud Test Instance
  DEV EBS
Roles
  Ankit - Coordinating sessions, Managing issue log, requirement review
  Goutham and Prurushottam – Continue with configurations, development; Support CRP sessions
  Gaurav - Design discussions
  Angio team - Validation

## Daywise (hidden)
Date | Location | Participants | Duration | Agenda
Day 1
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. User creation 2. Access management 3. Introduction to Supply chain planning and Oracle DM Cloud work Area
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Work with Page Layouts 2. Overview of Supply Chain Planning Plan Types
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Planning Analytics 2. Dimensions and Dimension Catalogs 3. Measure Catalog walk-thru
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1.5 | 1. Levels and Attributes 2. Measures in Supply Chain Planning 3. Configuring Demand Plan
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 0.5 | Capturing and discussing the issues identified during the day
Day 2
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Create and Manage DM Cloud Tables, Graphs 2. Manage Measure Data in Tables 3. View the Audit Trail for a Measure
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 2 | 1. Configuring new table 2. Adding different type of filters in the tables
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Angio specific setups and data validation: a) Angio Time, Product, Geo, Customer Dimensions b) Angio specific measures c) Angio tables
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Review of the data: a) Angio History Analysis - By Item and Org b) Angio History and Forecast Analysis - By GBU and Org c) Angio Forecast Analysis - By Customer
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 0.5 | Capturing and discussing the issues identified during the day
Day 3
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 2 | Data Review continued
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 2 | 1. NPI and Chaining process 2. What-If analysis - Simulation process
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 1 | Capturing and discussing the issues identified during the day
Day 4
2020-03-06 | PE Conference Room | Angio Team Triniti Team | 1 | Data Review continued
2020-03-06 | PE Conference Room | Angio Team Triniti Team | 1 | Review the final issue list

## Header
AIM
Quaterly Patch Testing Schedule
Triniti
Author | XX YY
Creation Date | 2020-12-01
Last Update Date | 2021-02-22
Version | 1.1
Change Record
Date | Author | Version | Change Reference
2020-12-01 | XX YY | 1 | New Document. No Previous Document

## Schedule
Assuming: JAN-MAR Quarterly Patch Cycle
Activity | Schedule | Stakeholders | Links and Remarks
New and Opt-in Expiration features review | Available next day after the last upgrade | IT Team | Refer the below link to review - https://www.oracle.com/webfolder/technetwork/tutorials/tutorial/readiness/offering.html
Test Plan Creation | By 01/28 | IT Team | Regression, Upgrade Specific and Opt In Expiration test cases
Review . New Features . Opt-in Expiration Features . Test Plan | Week of 02/01 | IT Team and Business Users | Review the features and test plan execution schedule in detail
Test Plan Approval | Week of 02/08 | Business Users | Business to approve the test case and its execution schedule
Patch Application: Non-Production Instance | 1st Friday of March | Oracle | Oracle shares the instance downtime details generally two weeks prior to the quarterly patch application date
Execute Test Plan | Two weeks to execute test cases | IT Team and Business Sanity Check | Execute the test plan
Result Review and Approval | After test plan execution, before 3rd Friday of March | IT Team and Business Users | In case if the testing fails, raise an SR with Oracle to stop the quarterly patch getting applied in the PROD instance
Patch Application: Production Instance | 3rd Friday of March | Oracle | Oracle shares the instance downtime details generally two weeks prior to the quarterly patch application date
Sanity Check Prod Instance | After Prod Patch Application | IT Team | IT team to do sanity check for the patch getting migrated to PROD instance